## Full Refresh
Step # | System | Step Name | Description | Responsible | Duration | Sandboxes | Comments
| ALL | Communicate to end users | Communicate refresh schedule and outage times to end users |  |  | Full Sandbox only
1 | SAP | Extract customer numbers | Extract customer numbers from SAP that is connected to the SFDC sandbox |  | 1 hour |  | Match against SFDC in step 16
2 | CINT | Halt updates | Stop integrations for period of refresh |  |  |  | Do we need to do this? Action : Check this out
3 | BW? | Halt BW load | Stop BW load for period of refresh |  |  |  | Do we need to do this? Action : Check this out
4 | SFDC | Initiate SFDC Sandbox Refresh | Do not copy Chatter or field history tracking | AM | Up to 24 hours | Full Sandbox only | Can't use templates. Sandbox must be activated after refresh process has completed before admins can log on.
5 | SFDC | Freeze users | Freeze all users except admins | AM | 30 mins | All | Do we want to freeze the integration user (yes)
6 | SFDC | Disable OBM | Update custom setting for OBM so they don't get sent until everything is verified | AM | 10 mins | All
7 | SFDC | Delete CS prod functional inboxes | Remove the production inboxes used in email-to-case | AM | 15 mins | All
8 | SFDC | Set-up new functional inboxes | Set up test functional inboxes and forwarding rules on those inboxes | PN / AM | 1 hour |  | Need assistance from PN inbox admins - not critical path
9 | SFDC | Live Agent Configuration | Point Live agent at the current sandbox as it will point to production. This has to be done by copying the url from the live agent deployments to the "Demo_Live_Agent" page. | AM | 15 mins | All
10 | SFDC | Update email deliverability settings | Navigate to Email Administration-->Deliverability and set the Access level to "System email" under Deliverability. | AM | 10 mins | All | This will stop emails going out to customers
11 | SFDC | Outbound Messaging | Set OBM endpoint to correct CINT environment | AM | 20 mins | All | Only 2 endpoints - CINT Prod and CINT AT
12 | SFDC | Outbound webservices endpoints | Set webservices endpoints (PAR, NTT, etc) | AM | 20 mins | All
13 | SFDC | Links | Check all links to make sure that customers can't log items to the sandbox | AM | 20 mins | All | View SAP Prices, View SAP Contracts buttons on account object - NOTE - check with Eva/business is there a test version as all sandboxes show prod link
14 | SFDC | Switch off triggers and validation rules | To ensure data work can be carried out without flagging rules | AM | 10 mins | Full Sandbox only
15 | SFDC | Master Data | Delete all possible duplicate association records | AM | 15 mins | Full Sandbox only | This is so that accounts can be deleted without causing a dependency exception
16 | SFDC | Master Data | Identify and delete data from date range not required | AM | 2 hours | Full Sandbox only | Date range to be between today and the last SAP refresh date. Use dataloader. Accounts & associated child objects, Contacts. NOTE - SFDC went live after the last SAP refresh - how do we match SAP to SFDC? Should we delete all Private persons from sandbox? DECISION : Delete all accounts with Private Person record type. Delete all accounts beginning with 9000 for first refresh. Accounts associated with cases couldn't be deleted - should we delete all cases or build a query to identify just the cases in question? Need to add Possible Duplicate Accounts to delete list - do before accounts.
17 | SFDC | Master Data | Scramble/clear customer email addresses | AM | 2 hours | Full Sandbox only | Use dataloader - Accounts and contacts - do we need to scramble bank details? No scramble of bank details. Delete all customer emails.
18 | SFDC | Data | Delete private opportunities and account plans | AM | 30 mins | Full Sandbox only | Use dataloader - remove opps with private flag = true. Delete all account plans (object is SFDC_Acct_Plan__c).
19 | SFDC | Data | Remove events and all attachments/files | AM | 30 mins | Full Sandbox only | Chatter should not come with refresh. Delete all attachments. Delete all events.
20 | SFDC | Switch on triggers and validation rules | To be done when data work is complete | AM | 10 mins | Full Sandbox only
21 | SFDC | Reset involved party id range |  | AM | 10 mins | All | NOTE : need to discuss how customer numbring will work in Stg for 2nd refresh onwards
22 | SFDC | Schedule Batch Apex | Check batch jobs are scheduled |  | 10 mins | All
23 | SFDC | Manage users | Unfreeze integration users | AM | 30 mins | Full Sandbox only
24 | CINT | Connect to sandbox | Use stg credentials | CINT | 30 mins | Full Sandbox only
25 | SFDC | Enable OBM | Update custom setting for OBM so that OBM's can be sent | AM | 10 mins | Full Sandbox only
26 | SFDC | Verification | Run through documented SFDC verification steps | AM | 1 hour | All
27 | SFDC/CINT/SAP | Verification of customer replication | Verify customer is sent to CINT and on to SAP. Verify webshop pool process. | AM/PN | 1 hour | Full Sandbox only
28 | Marketo | Marketo sandbox refresh | All manual steps |  | ? |  | Can be done independently of any other refresh - should be done when SFDC refresh is done. Workspace conflicts?
29 | CINT | Begin updates | Once refresh is complete |  |  |  | Do we need to do this? Action : Check this out
30 | BW? | Begin BW load | Once refresh is complete |  |  |  | Do we need to do this? Action : Check this out

## Full step details
Step # | Detailed Instructions
5 | 1. Use Dataloader to export all users using this query : Select Id, UserId, IsFrozen FROM UserLogin WHERE UserId IN (Select Id FROM User Where isActive = true AND Profile.Name != 'System Administrator' AND Profile.Name != 'Postnord System Administrator') AND IsFrozen = false 2. Update IsFrozen to TRUE and save csv 3. Use dataloader to update UserLogin with csv 4. Spot check that Admins are not frozen and other users are frozen
6 | 1. Go to Setup->Develop->Custom Settings. 2. Click on the "Manage" link next to the custom setting called DisableAutomation. 3. Click the edit button at the top of the custom setting. 4. Tick the "Disable All OBM Workflows" box and press Save. 5. Delete the setting for all that are not one of the following : 1) Profile: Integration User 2) Profile: Integration Read Only User 3) Profile: Integration Exposed Webservices User 4) User: Data Quality User All should have Disable OBM set to True
7 | 1. Go to Setup->Customise->Cases->Email to Case. 2. Delete all entries in the "Routing Addresses" section
9 | 1. Go to Setup->Customise->Live Agent->Settings. 2. Update the Live Agent API Endpoint to https://d.la2w1cs.salesforceliveagent.com/chat/rest/. 3. Go to Setup->Customise->Live Agent->Deployments 4. Click on the Live Agent DK link. 5. Make sure the first piece of the Deployment Code looks like this - <script type='text/javascript' src='https://c.la2w1cs.salesforceliveagent.com/content/g/js/30.0/deployment.js'></script> <script type='text/javascript'> liveagent.init('https://d.la2w1cs.salesforceliveagent.com/chat', (there will be some script after this piece - that is OK as it is 6. Copy the deployment code from Live Agent DK deployment. 7. Go to Setup->Develop->Pages and edit page DEMO_Live_Agent 8. Replace lines 2-5 with the deployment code you copied in step 6
10 | 1. Go to Setup->Email Administration->Deliverability 2. Set the Access Level in the Access to Send Email section to "System email only" and click Save
11 | 1. Create a change set from another dev environment - put all Workflow Outbound Message components in it 2. Deploy change set to environment you have refreshed
12 | 1. Retrive file HTTP Integration Services - CINT AT from GIT 2. Delete records in custom setting HTTP Integration Services 3. Load the file using data loader to object HTTP_Integration_services__c
14 | 1. Go to Setup->Develop->Custom Settings. 2. Click on the "Manage" link next to the custom setting called DisableAutomation. 3. Click the edit button at the top of the custom setting. 4. Tick the "Disable All Validation Rules" and "Disable All Triggers" boxes and press Save.
15 | 1. Use dataloader to export all records from the Possible Duplicate Account Association object 2. Use file to delete all records using dataloader
16 | 1. Export all accounts according to this query : Select Id, Record_Type_Developer_Name__c, Involved_Party_ID__c, Deletion_Flag__c FROM Account WHERE Record_Type_Developer_Name__c = 'PersonAccount' OR Involved_Party_ID__c like '90%' 2. Switch off triggers in Custom setting Disable Automation 3. Switch off validation rules in Disable Automation custom setting 4. Use the fiel output in step 1 to perform a delete using data loader 5. Switch All Triggers and All validation rules back on in Disbale Automation custom setting
17 | 1. Use the following query in dataloader to extract accounts to update - Select Id, PersonEmail, Additional_Email_Address_1__c, Additional_Email_Address_2__c, Email_Address__c, Additional_Email_Address__pc FROM Account WHERE Email_Address__c != '' OR Additional_Email_Address_1__c != '' OR Additional_Email_Address_2__c != '' OR Additional_Email_Address__pc != '' OR PersonEmail != '' 2. Blank all email address fields and use file to run update on account in data loader - please remember these extra settings needed in dataloader to insert null values to a field - http://help.salesforce.com/apex/HTViewSolution?id=000005442&language=en_US 3. Repeat with query - Select Id, Email, Additional_Email_Address__c FROM Contact WHERE Additional_Email_Address__c != '' OR Email != '' - for contacts
18 | 1. Use dataloader to export opportunities where Private_Opportunity__c is TRUE - Select Id FROM Opportunity WHERE Private_Opportunity__c = TRUE 2. Delete opportunities using export file as input to dataloader 3. Export all records from Customer Plan object using dataloader 4. Perform delete using data loader on Customer Plan object
19 | 1. Use dataloader to export events 2. Delete events using export file as input to dataloader 3. Export all attachments using dataloader 4. Perform delete using data loader on attachments
20 | 1. Go to Setup->Develop->Custom Settings. 2. Click on the "Manage" link next to the custom setting called DisableAutomation. 3. Click the edit button at the top of the custom setting. 4. Untick the "Disable All Validation Rules" and "Disable All Triggers" boxes and press Save.
21 | When deploying the objects Involved Party ID Range and Internal Involved Party ID Range make sure the Name (Auto-number) is generating a number in the correct number range on both of those objects. The correct number ranges are: Involved Party ID Range: 90 000 000 Internal Involved Party ID Range: 41 000 000 If the number ranges are not correct, here is a fix: 1. Change the Name data type from Auto Number to Text (On both the objects), Save. 2. Change the Name data type back from Text to Auto Number setting the correct starting number The number ranges will now start from the starting number you set.
22 | 1. Go to setup->Develop->Custom Settings. 2. Click Manage on ScheduledJobParameters 3. Edit AccountTeamMemberSyncJobId and deletionJobId and set them to blank
23 | Manually unfreeze the following users : integration.crmwebservice@post.dk.get2onestg integration.obmfromcrm@post.dk.get2onestg integration.readonly@post.dk.get2onestg integration.realtimeupsert@post.dk.get2onestg integration.scheduledquery@post.dk.get2onestg integration.scheduledupsert@post.dk.get2onestg